## June_Planner
Date | Day | Activity Planned | Activity-1 Status | Activity-2 Status | Activity-3 Status
2017-06-19 | Monday | 1. Getting Familiar with MIRC, MyPACS and RedLex websites/data 2. Studying the data and understanding its features 3. Familiarizing the Py script used to generate this data | Complete | Complete | In Progress
2017-06-20 | Tuesday | 1. Understanding the coverage of Radlex terms for each of the 5 important category of MIRC teaching files with codes written by Sungmin and Priya team 2. Understanding and confirming the task I need to perform with Prof. Raicu (If it is the same coverage details expected or something different) 3. Plan my coding activity for the task assigned | Complete | Complete | Complete
2017-06-21 | Wednesday | 1. Write or reuse the code to calculate the coverage of Radlex terms (activity assigned after being confirmed with Prof. Raicu) | Complete | Complete | Complete
2017-06-22 | Thursday | 1. Review the results with Priya 2. Prepare the output 3. Prepare presentation for Friday meeting | Complete | Complete | Complete
2017-06-23 | Friday | 1. Presentation and weekly update 2. Understand the mistake or missing works through Prof comments 3. Work on those comments in rectifying them and finalize the task that needs to be done for next week | Complete | Complete | Complete
2017-06-24 | Saturday
2017-06-25 | Sunday
2017-06-26 | Monday | 1. Email Sugmin requesting for all latest codes used and follow up on that. 2. Familiarize with BioPortal and sub categories to understand the dedogram generated by Priya team and what is reproduced by self 3. Send the results obtained to Priya and continue to familiarize the Py script used to generate this data
2017-06-27 | Tuesday | 1. Confirm how word frequencies are encoded is it with TFID or Entropy 2. Confirm if the cluster results obtained is only part of a particular category or the whole MIRC website 3. Interpret the result and do a small write-up and continue to familiarize the Py scipt from previous day
2017-06-28 | Wednesday | 1. Meeting with Prof and showcase the work done till this week and get it validated and understand the direction to work for fridays meet. 2. Work on the results reproduced much more and get more comfortable 3. Try to do the writeup based on the results obtained from MIRC and get comfortable with Py code written
2017-06-29 | Thursday | 1. Get the writing validated and reviewed from Priya 2. Prepare to walk through the code once and the cluster results obtained, understand what is entropy and why entropy is used as a parameter, etc., 3. Complete the presentation for Fridays meeting
2017-06-30 | Friday | 1. Presentation and weekly update, try to show the report return so far and walk through the code if possible. 2. Understand the mistake or missing works through Prof comments 3. Work on those comments in rectifying them and finalize the task that needs to be done for next week
2017-07-01 | Saturday
2017-07-02 | Sunday

## June2017
Date | 2017-06-16
SINO | Task
1 | Attended first team meeting for this term
2 | There where 4 project on which the update was given
1. Matth presentation on LIDC project
2. Priya Presentation on MIRC Smart Search project
3. Caroline Presentation on Search engine being built
4. Srirams Presentation on image based search engine
3 | I am alloted to work on Natural Language processing of smart search project for MyPacs data
1. Prof assigned me the task to see or calculate the coverage of Radlex terms for each category like:
a. Clinical findings
b. Diagonosis, etc.,
4 | Had a short discussion with Priya in understanding the high level view of this project from her cubicle in the 8th floor.
1. Priya's mobile number is +16308632175
2. Project is more based on Python, web scrapping, natural language processing, image based search engine to provide Radiologist to provide one single platform to perform their validation
3. Validation file is the patient file recorded from CT or MRA ot X-Ray, etc., which is validated against its respective teaching file resposity available in RadLex and Oxford Medical Dictionary
| 4. Context based text search |  |  | This covers | Synonyms | Negation | Adjectives | Hyrarchial Text Structure | Proximity of Words
| 5. Content absed image search |  |  | SIFT Indicator (Segmentation) |  | Patch Based Descriptor |  | Region Based Descriptors
6. Hybrid text and image search
5 | Received the data for MIRC and its reference code from Priya
6 | Did a local back up on GitHub
7 | Installed Anaconda for Python in local system
8 | Installed GitHub in local system for version maintanance
Date | 2017-06-19
SINO | Task
1 | MIRC is a website which has the repository of all teaching files maintained by RSNA Informatics, these are available in http://mirc.rsna.org/query
1. This teaching file repository consist of following details listed
a. Title - Teaching File Titles
b. Library - Package under which cases these teaching files are present and packed, generall the hospital name or institution name (there are totally 23 distinct libraries)
c. Author - Author of the teaching file, it can be the name of the hospital or Institution or the radiologist who created this teaching file
d. Speciality - Clinical area of speaciality to which these teaching files belong to
e. Date Modified - Date when it is last modified with adding new images or updating/deleting old images
f. Date Created - Date on which the specific teaching files are created initially based on the title
g. Access - Access permission given, it is either (Public, Restricted and Private(owners only)
2. This website has a search box, where we can search for any teaching file which we need for reference. However, the gap with this search is that it is a simple database queary which is happening in RSNA backend and fetch all queary with a wild card select search.
3. For e.g. search for 'Renal artery aneurysms in Neurofibromatosis' in search box and click enter, this will be a wild card search result
4. There is no natural language processing here, that is if we search for 'No Renal artery aneurysms in Neurofibromatosis' even then the search results are same
5. For few tiltles like 'Renal artery aneurysms in Neurofibromatosis' there are also duplicate records fetched, few cases may be real duplicates which few may not be duplicate, this needs to be handled as I see this would affect term frequency parameter
6. There is also an advance search option which is again a wild card search but involving one or more collumn from RSNA database. So, search results at some case are mostly not relavant
7. Our Project is trying to close this gap and building an ability to provide a search window which also does natural language processing not only from the data available from RSNA MIRC but also from other similar websites like MyPACS, etc., This is the high level requirement
2 | Each Title is linked to an XML file and this XML file consist of below elements in them:
a. Document
1. Data Source - This variable is made up
2. Title - Title of the teaching file is derived from <title> tag
3. Authors - Person who created teaching file, it is derived form <p class="authorname"> tag
4. Date Created - it is derived from <p class="center"> and "Publication Date:"
b. History
c. Findings
d. Diagnosis
e. DDx
f. Discussion
g. References
h. RadLex Term
i. RadLex Term URL
j. URL

## Sheet1
Date | Day | Activity Planned | Activity-1 Status | Activity-2 Status | Activity-3 Status
2017-06-26 | Monday | 1. Email Sugmin requesting for all latest codes used and follow up on that. 2. Familiarize with BioPortal and sub categories to understand the dedogram generated by Priya team and what is reproduced by self 3. Send the results obtained to Priya and continue to familiarize the Py script used to generate this data
2017-06-27 | Tuesday | 1. Confirm how word frequencies are encoded is it with TFID or Entropy 2. Confirm if the cluster results obtained is only part of a particular category or the whole MIRC website 3. Interpret the result and do a small write-up and continue to familiarize the Py scipt from previous day
2017-06-28 | Wednesday | 1. Meeting with Prof and showcase the work done till this week and get it validated and understand the direction to work for fridays meet. 2. Work on the results reproduced much more and get more comfortable 3. Try to do the writeup based on the results obtained from MIRC and get comfortable with Py code written
2017-06-29 | Thursday | 1. Get the writing validated and reviewed from Priya 2. Prepare to walk through the code once and the cluster results obtained, understand what is entropy and why entropy is used as a parameter, etc., 3. Complete the presentation for Fridays meeting
2017-06-30 | Friday | 1. Presentation and weekly update, try to show the report return so far and walk through the code if possible. 2. Understand the mistake or missing works through Prof comments 3. Work on those comments in rectifying them and finalize the task that needs to be done for next week