## June_Planner
Date | Day | Activity Planned | Activity-1 Status | Activity-2 Status | Activity-3 Status
2017-06-19 | Monday | 1. Getting Familiar with MIRC, MyPACS and RedLex websites/data 2. Studying the data and understanding its features 3. Familiarizing the Py script used to generate this data | Complete | Complete | In Progress
2017-06-20 | Tuesday | 1. Understanding the coverage of Radlex terms for each of the 5 important category of MIRC teaching files with codes written by Sungmin and Priya team 2. Understanding and confirming the task I need to perform with Prof. Raicu (If it is the same coverage details expected or something different) 3. Plan my coding activity for the task assigned | Complete | Complete | Complete
2017-06-21 | Wednesday | 1. Write or reuse the code to calculate the coverage of Radlex terms (activity assigned after being confirmed with Prof. Raicu) | Complete | Complete | Complete
2017-06-22 | Thursday | 1. Review the results with Priya 2. Prepare the output 3. Prepare presentation for Friday meeting | In Progress | Complete | Complete
2017-06-23 | Friday | 1. Presentation and weekly update 2. Understand the mistake or missing works through Prof comments 3. Work on those comments in rectifying them and finalize the task that needs to be done for next week | In Progress
2017-06-24 | Saturday
2017-06-25 | Sunday
2017-06-26 | Monday
2017-06-27 | Tuesday
2017-06-28 | Wednesday
2017-06-29 | Thursday
2017-06-30 | Friday
2017-07-01 | Saturday
2017-07-02 | Sunday

## June2017
Date | 2017-06-16
SINO | Task
1 | Attended first team meeting for this term
2 | There where 4 project on which the update was given
1. Matth presentation on LIDC project
2. Priya Presentation on MIRC Smart Search project
3. Caroline Presentation on Search engine being built
4. Srirams Presentation on image based search engine
3 | I am alloted to work on Natural Language processing of smart search project for MyPacs data
1. Prof assigned me the task to see or calculate the coverage of Radlex terms for each category like:
a. Clinical findings
b. Diagonosis, etc.,
4 | Had a short discussion with Priya in understanding the high level view of this project from her cubicle in the 8th floor.
1. Priya's mobile number is +16308632175
2. Project is more based on Python, web scrapping, natural language processing, image based search engine to provide Radiologist to provide one single platform to perform their validation
3. Validation file is the patient file recorded from CT or MRA ot X-Ray, etc., which is validated against its respective teaching file resposity available in RadLex and Oxford Medical Dictionary
| 4. Context based text search |  |  | This covers | Synonyms | Negation | Adjectives | Hyrarchial Text Structure | Proximity of Words
| 5. Content absed image search |  |  | SIFT Indicator (Segmentation) |  | Patch Based Descriptor |  | Region Based Descriptors
6. Hybrid text and image search
5 | Received the data for MIRC and its reference code from Priya
6 | Did a local back up on GitHub
7 | Installed Anaconda for Python in local system
8 | Installed GitHub in local system for version maintanance
Date | 2017-06-19
SINO | Task
1 | MIRC is a website which has the repository of all teaching files maintained by RSNA Informatics, these are available in http://mirc.rsna.org/query
1. This teaching file repository consist of following details listed
a. Title - Teaching File Titles
b. Library - Package under which cases these teaching files are present and packed, generall the hospital name or institution name (there are totally 23 distinct libraries)
c. Author - Author of the teaching file, it can be the name of the hospital or Institution or the radiologist who created this teaching file
d. Speciality - Clinical area of speaciality to which these teaching files belong to
e. Date Modified - Date when it is last modified with adding new images or updating/deleting old images
f. Date Created - Date on which the specific teaching files are created initially based on the title
g. Access - Access permission given, it is either (Public, Restricted and Private(owners only)
2. This website has a search box, where we can search for any teaching file which we need for reference. However, the gap with this search is that it is a simple database queary which is happening in RSNA backend and fetch all queary with a wild card select search.
3. For e.g. search for 'Renal artery aneurysms in Neurofibromatosis' in search box and click enter, this will be a wild card search result
4. There is no natural language processing here, that is if we search for 'No Renal artery aneurysms in Neurofibromatosis' even then the search results are same
5. For few tiltles like 'Renal artery aneurysms in Neurofibromatosis' there are also duplicate records fetched, few cases may be real duplicates which few may not be duplicate, this needs to be handled as I see this would affect term frequency parameter
6. There is also an advance search option which is again a wild card search but involving one or more collumn from RSNA database. So, search results at some case are mostly not relavant
7. Our Project is trying to close this gap and building an ability to provide a search window which also does natural language processing not only from the data available from RSNA MIRC but also from other similar websites like MyPACS, etc., This is the high level requirement
2 | Each Title is linked to an XML file and this XML file consist of below elements in them:
a. Document
1. Data Source - This variable is made up
2. Title - Title of the teaching file is derived from <title> tag
3. Authors - Person who created teaching file, it is derived form <p class="authorname"> tag
4. Date Created - it is derived from <p class="center"> and "Publication Date:"
b. History
c. Findings
d. Diagnosis
e. DDx
f. Discussion
g. References
h. RadLex Term
i. RadLex Term URL
j. URL