## June_Planner
Date | Day | Activity Planned | Activity-1 Status | Activity-2 Status | Activity-3 Status
2017-06-19 | Monday | 1. Getting Familiar with MIRC, MyPACS and RedLex websites/data 2. Studying the data and understanding its features 3. Familiarizing the Py script used to generate this data | Complete | Complete | In Progress
2017-06-20 | Tuesday | 1. Understanding the coverage of Radlex terms for each of the 5 important category of MIRC teaching files with codes written by Priya 2. Understanding and confirming the task I need to perform with Prof. Raicu (If it is the same coverage details expected or something different) 3. Plan my coding activity for the task assigned | In Progress | Complete
2017-06-21 | Wednesday | 1. Write or reuse the code to calculate the coverage of Radlex terms (activity assigned after being confirmed with Prof. Raicu)
2017-06-22 | Thursday | 1. Review the results with Priya 2. Prepare the output 3. Prepare presentation for Friday meeting
2017-06-23 | Friday | 1. Presentation and weekly update 2. Understand the mistake or missing works through Prof comments 3. Work on those comments in rectifying them and finalize the task that needs to be done for next week
2017-06-24 | Saturday
2017-06-25 | Sunday
2017-06-26 | Monday
2017-06-27 | Tuesday
2017-06-28 | Wednesday
2017-06-29 | Thursday
2017-06-30 | Friday
2017-07-01 | Saturday
2017-07-02 | Sunday

## June2017
Date | 2017-06-16
SINO | Task
1 | Attended first team meeting for this term
2 | There where 4 project on which the update was given
1. Matth presentation on LIDC project
2. Priya Presentation on MIRC Smart Search project
3. Caroline Presentation on Search engine being built
4. Srirams Presentation on image based search engine
3 | I am alloted to work on Natural Language processing of smart search project for MyPacs data
1. Prof assigned me the task to see or calculate the coverage of Radlex terms for each category like:
a. Clinical findings
b. Diagonosis, etc.,
4 | Had a short discussion with Priya in understanding the high level view of this project from her cubicle in the 8th floor.
1. Priya's mobile number is +16308632175
2. Project is more based on Python, web scrapping, natural language processing, image based search engine to provide Radiologist to provide one single platform to perform their validation
3. Validation file is the patient file recorded from CT or MRA ot X-Ray, etc., which is validated against its respective teaching file resposity available in RadLex and Oxford Medical Dictionary
| 4. Context based text search |  | This covers | Synonyms | Negation | Adjectives | Hyrarchial Text Structure | Proximity of Words
| 5. Content absed image search |  | SIFT Indicator (Segmentation) |  | Patch Based Descriptor |  | Region Based Descriptors
6. Hybrid text and image search
5 | Received the data for MIRC and its reference code from Priya
6 | Did a local back up on GitHub
7 | Installed Anaconda for Python in local system
8 | Installed GitHub in local system for version maintanance
Date | 2017-06-19
SINO | Task